## Course Project Checkup
|  |  | Sprint 1 |  |  | Sprint 2
|  |  | Goal: Establish a basic foundation for the company website |  |  | Goal: Improve the website through fine detail adjustments
|  |  | Start = October 25 |  |  | Start = November 1
|  |  | End = October 31 |  |  | End = November 7
|  |  | Planned Velocity = 2 |  |  | Planned Velocity = 2
Product Backlog |  |  | Actual Velocity = 0 |  |  | Actual Velocity = 0
Work Item | Estimate | Priority | Priority | Incomplete | Done? | Priority | Incomplete | Done?
As a business owner I want a website so that it can promote my jewelry reselling business | 70 | High | High | Y | N | High | Y | N
A a customer I want to be able to interact and scroll through the website so that I can see what it has to offer | 20 | High | High | Y | N | High | Y | N
As a customer I want to be able to submit an inquiry so that I can reach out to the owner if I am interested in doing business | 40 | Medium | Medium | Y | N | Medium | Y | N
Sprint 1 Backlog
|  |  | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Tasks (User stories highlighted in yellow) | Owner | Status | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31
As a business owner I want a website so that it can promote my jewelry reselling business | Kevin Zhang | In Progress | 11 | 11 | 11 | 8 | 0 | 0 | 0
Create the first page of the website | Kevin Zhang | In Progress | 9 | 9 | 9 | 7 | 0 | 0 | 0
Find a domain or server to host the website | Kevin Zhang | In Progress | 2 | 2 | 2 | 1 | 0 | 0 | 0
A a customer I want to be able to interact and scroll through the website so that I can see what it has to offer | Kevin Zhang | In Progress | 6 | 6 | 6 | 4 | 0 | 0 | 0
Create the website in correct HTML and CSS format | Kevin Zhang | In Progress | 5 | 5 | 5 | 3 | 0 | 0 | 0
Ensure that there are no syntax errors | Kevin Zhang | In Progress | 1 | 1 | 1 | 1 | 0 | 0 | 0
As a customer I want to be able to submit an inquiry so that I can reach out to the owner if I am interested in doing business | Kevin Zhang | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a text box that allows the user to type an inquiry in and submit it | Kevin Zhang | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ensure that I can recieve the inquiry on my end of the server | Kevin Zhang | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 2 Backlog
|  |  | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Tasks (User stories highlighted in yellow) | Owner | Status | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07
As a business owner I want a website so that it can promote my jewelry reselling business | Kevin Zhang | In Progress | 11 | 11 | 11 | 11 | 11 | 5 | 0
Create the first page of the website | Kevin Zhang | In Progress | 10 | 10 | 10 | 10 | 10 | 4 | 0
Find a domain or server to host the website | Kevin Zhang | In Progress | 1 | 1 | 1 | 1 | 1 | 1 | 0
A a customer I want to be able to interact and scroll through the website so that I can see what it has to offer | Kevin Zhang | In Progress | 14 | 14 | 14 | 14 | 14 | 6 | 0
Create the website in correct HTML and CSS format | Kevin Zhang | In Progress | 12 | 12 | 12 | 12 | 12 | 5 | 0
Ensure that there are no syntax errors | Kevin Zhang | In Progress | 2 | 2 | 2 | 2 | 2 | 1 | 0
As a customer I want to be able to submit an inquiry so that I can reach out to the owner if I am interested in doing business | Kevin Zhang | In Progress | 4 | 4 | 4 | 4 | 4 | 2 | 0
Create a text box that allows the user to type an inquiry in and submit it | Kevin Zhang | In Progress | 4 | 4 | 4 | 4 | 4 | 2 | 0
Ensure that I can recieve the inquiry on my end of the server | Kevin Zhang | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Simple Model
A Simple Model for the Mechanisms of the Website

## Product Backlog
|  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6 |  |  | Sprint 7
Release Plan: Since this is a personal project that does not have any outside customers so far, the only stakeholder is me. Thus, I am both the product owner and the stakeholder of this project. Each time I finish a Sprint and a work item, it doesn't really get released to me the customer, because I already am the customer and I already see and know everything. Therefore, there's no such thing as planning before release. I did use MVP in some parts of this project. For instance, all of the webpages are not fully complete, they lack interactive graphics and other features to entice customers, but at least I provided the MVP for the webpages that allow me to understand more about my interest and what additional features I want now that the minimum is complete. Therefore, my future plans for the webpages are documented in the Future Plan document and the future value deliveries are all listed there. |  |  | Goal: Create the About Page of the Website and write the first three sections of the business plan |  |  | Goal: Figure out what web hosting service I should choose for the website, which IDE should be used for continued development, make Contant Us Page of website |  |  | Goal: Create Submit Inquiry Page of Website, figure out advertising plans for the company, |  |  | Goal: Create Sales Page of Website and Menu toolbars for all the pages |  |  | Goal: Create Future Plans for this project and website, add remaining sections to business plan
|  |  | Start = November 8 |  |  | Start = November 15 |  |  | Start = November 22 |  |  | Start = November 29 |  |  | Start = December 6
|  |  | End = November 14 |  |  | End = November 21 |  |  | End = November 28 |  |  | End = December 5 |  |  | End = December 9
|  |  | Planned Velocity = 4 |  |  | Planned Velocity = 4 |  |  | Planned Velocity = 5 |  |  | Planned Velocity = 4 |  |  | Planned Velocity = 4
Epics and User Stories (Epics highlighted in yellow) |  |  | Actual Velocity = 4 |  |  | Actual Velocity = 4 |  |  | Actual Velocity = 3 |  |  | Actual Velocity = 2 |  |  | Actual Velocity = 4
Work Item | Estimate | Priority | Priority | Incomplete | Done? | Priority | Incomplete | Done? | Priority | Incomplete | Done? | Priority | Incomplete | Done? | Priority | Incomplete | Done? | Conditions of Satisfaction
Create the Contact Page of Website | 10 | Low | Low | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y
As a potential client, I want the email address to be a mailto hyperlink so that I can easily send an email with a simple click | 5 | Low | Low | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | The email address should open up a mailto draft on my computer when I click on the hyperlink
As a potential client, I want the phone number to be a hyperlink if on a mobile device so that I can easily call the number with a simple tap | 5 | Low | Low | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | My mobile phone should prompt me on whether I want to call the phone number listed when I tap on the phone number on the website
Create the Sales Page of Website | 80 | High | Medium | Y | N | Medium | Y | N | Medium | Y | N | High | Y | N | Medium | Y | N
As the business owner, I want a basic HTML outline on how the sales page should display each of its sales so that I can know how to list the jewelry on sale | 70 | High | Medium | Y | N | Medium | Y | N | Medium | Y | N | High | Y | N | Medium | Y | N | I should be able to see a list of all the jewelry for sale, its prices, and the carat weight of the gems
As a potential client, I want instructions on how to navigate the sales page so that I will know how to do that | 10 | High | Medium | Y | N | Medium | Y | N | Medium | Y | N | High | Y | N | Medium | Y | N | I should be able to know how to navigate the sales page after I read the instructions
Create the Submit an Inquiry Page of Website | 50 | Medium | Medium | Y | N | Medium | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y
As a potential seller, I want text boxes so that I can type my inquiry and other info in | 40 | Medium | Medium | Y | N | Medium | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | I should be able to type into those text boxes
As a potential seller, I want the business owner to be able to recieve the inquiry once I submit so that he can follow up | 60 | Medium | Medium | Y | N | Medium | Y | N | High | Y | N | Low | Y | N | Low | Y | N | I should receive the inquiry submission on the server side once it is submitted
As a potential seller, I want a copy of my inquiry to be sent to my email address | 60 | Medium | Medium | Y | N | Medium | Y | N | High | Y | N | Low | Y | N | Low | Y | N | The server should send a copy of the inquiry to the email address entered into the form
Create the About Page of Website | 30 | Medium | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y
As a potential client, I want a set of paragraphs giving me a rundown to this company so that I can know what this is all about | 25 | Medium | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | I should know about the jewelry trading company based on reading what's on the about page
Find the ECommerce Hosting Platform for the Website | 8 | Low | Low | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y
As a business owner, I want to contract a web hosting service so that I can host my website online where potential clients can access it | 8 | Low | Low | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | There should be a plan as to how I am going to host the website on the internet
Find a Web Development IDE Platform for the Website | 20 | High | High | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y
As a business owner, I want a web development IDE platform so that I can develop my website using this tool while it is still under development | 20 | High | High | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | I should have a web development IDE that I will use in the long term to develop and test any changes to the website
Develop a Future Plan for Building the Website | 30 | Low | Low | Y | N | Low | Y | N | Low | Y | N | Low | Y | N | High | N | Y
As a business owner, I want a list of what remaining backlog for this website still needs to be finished after this course ends so that I will know what to continue to work on | 20 | Low | Low | Y | N | Low | Y | N | Low | Y | N | Low | Y | N | High | N | Y | There should be a backlog that covers all the remaining tasks that were not finished for the project
As a business owner, I want a list of proposed additional features for this website so that I can start thinking about what else to add on to the website | 20 | Low | Low | Y | N | Low | Y | N | Low | Y | N | Low | Y | N | High | N | Y | There should be a list of additional website features that would help in improving the quality and appearance
Advertising to Customers | 30 | Low | Low | Y | N | Medium | Y | N | High | Y | N | Medium | Y | N | Medium | N | Y
As the business owner, I want an advertisement image to display so that I can attract potential clients | 10 | Low | Low | Y | N | Medium | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | I successfully find at least one image to serve as my advertisement
As the business owner, I want some catchy advertising phrases so that I can attract potential clients | 15 | Low | Low | Y | N | Medium | Y | N | High | N | Y | N/A | N | Y | N/A | N | Y | I successfully come up with at least one catchy phrase to put onto my advertisement
Create a Menu Toolbar for all Pages of the Website | 60 | Medium | Low | Y | N | Low | Y | N | Low | N | Y | High | N | Y | N/A | N | Y
As the business owner, I want the menu toolbar to display buttons to all the webpages so that the user may navigate to the desired page | 30 | Medium | Low | Y | N | Low | Y | N | Low | N | Y | High | N | Y | N/A | N | Y | All of the webpages must have the menu toolbar that when clicked on will navigate to the webpage
As the business owner, I want the menu toolbar to have a catchy appearance so that the user can easily see and use it | 50 | Medium | Low | Y | N | Low | Y | N | Low | N | Y | High | N | Y | N/A | N | Y | The menu toolbar must be easily visible and hard to miss for the average person
Make a Business Plan | 90 | High | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | High | N | Y
As a business owner, I want a market analysis section in the business plan so that I can keep track of my analysis of the overall jewelry marketplace | 30 | High | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | The market analysis section is satisfactorily completed with enough key points addressed
As a business owner, I want a organization and management section in the business plan so that I can know how this business will be organized | 20 | High | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | The organization and management section is satisfactorily completed with enough key points addressed
As a business owner, I want a service section in the business plan so that I can keep a precise definition of what service I am offering to my clients | 20 | High | High | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | N/A | N | Y | The service section is satisfactorily completed with enough key points addressed
As a business owner, I want a marketing and sales section in the business plan so that I can know how I plan to market and sell my jewelry | 30 | High | Medium | Y | N | Medium | Y | N | Medium | Y | N | Medium | Y | N | High | N | Y | The marketing and sales section is satisfactorily completed with enough key points addressed
As a business owner, I want a funding plan section in the business plan so that I can know how I plan to fund my company | 20 | High | Medium | Y | N | Medium | Y | N | Medium | Y | N | Medium | Y | N | High | N | Y | The funding plan section is satisfactorily completed with enough key points addressed

## Sprint Backlogs
Sprint 3 Backlog | [9 empty] | Sprint 4 Backlog
|  |  | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday |  |  |  | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Tasks (User stories highlighted in yellow) | Owner | Status | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | Tasks (User stories highlighted in yellow) | Owner | Status | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21
As a potential client, I want a set of paragraphs giving me a rundown to this company so that I can know what this is all about | Kevin Zhang | Completed | 3 | 3 | 3 | 0 | 0 | 0 | 0 | As a business owner, I want to contract a web hosting service so that I can host my website online where potential clients can access it | Kevin Zhang | Completed | 6 | 6 | 6 | 6 | 0 | 0 | 0
Write the HTML source code for the about webpage | Kevin Zhang | Completed | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | Research potential web hosting services | Kevin Zhang | Completed | 2 | 2 | 2 | 2 | 0 | 0 | 0
Proofread the webpage to ensure it is satisfactory | Kevin Zhang | Completed | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Select the web hosting service I want and document the reason why | Kevin Zhang | Completed | 4 | 4 | 4 | 4 | 0 | 0 | 0
As a business owner, I want a market analysis section in the business plan so that I can keep track of my analysis of the overall jewelry marketplace | Kevin Zhang | Completed | 5 | 5 | 5 | 3 | 0 | 0 | 0 | As a business owner, I want a web development IDE platform so that I can develop my website using this tool while it is still under development | Kevin Zhang | Completed | 8 | 8 | 8 | 5 | 0 | 0 | 0
Research about the jewelry market | Kevin Zhang | Completed | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Research potential web development IDE platforms | Kevin Zhang | Completed | 5 | 5 | 5 | 2 | 0 | 0 | 0
Document the research findings in a market analysis | Kevin Zhang | Completed | 3 | 3 | 3 | 3 | 0 | 0 | 0 | Select the IDE platform I want and document the reason why | Kevin Zhang | Completed | 3 | 3 | 3 | 3 | 0 | 0 | 0
As a business owner, I want a organization and management section in the business plan so that I can know how this business will be organized | Kevin Zhang | Completed | 3 | 3 | 3 | 3 | 0 | 0 | 0 | As a potential client, I want the email address to be a mailto hyperlink so that I can easily send an email with a simple click | Kevin Zhang | Completed | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
As a business owner, I want a service section in the business plan so that I can keep a precise definition of what service I am offering to my clients | Kevin Zhang | Completed | 2 | 2 | 2 | 2 | 0 | 0 | 0 | As a potential client, I want the phone number to be a hyperlink if on a mobile device so that I can easily call the number with a simple tap | Kevin Zhang | Completed | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Results from Sprint 3: | [9 empty] | Results from Sprint 4:
I was able to finish all the backlog tasks that were assigned for this Sprint. From this Sprint, I was able to complete the About webpage of the website as well as the market analysis, organization and management, and service sections of the business plan. This was mostly because all these tasks were pretty easy and straightforward. They weren't tasks where I had the possibility of running into any software bugs that could halt my progress. I was able to learn a little bit more about how HTML works as well as the jewelry market in America and what are the current trends of the jewelry market. I also now have an overview in my head about how to organize and manage my company in the future. | [9 empty] | I was able to finish all the backlog tasks that were assigned for this Sprint. This was mostly because all these tasks, while some were a bit more complicated than Sprint 3, were still pretty straightforward. I completed the Contact Us web page and decided what web hosting server and IDE platform I would use for this website going forward. From this Sprint, I learned about how hyperlinks in HTML work, how to find a good web hosting service for your business, and I also learned about a great online IDE platform called codepen.io that I will use from now on to store and manage my development of the website.
Sprint 5 Backlog | [9 empty] | Sprint 6 Backlog
|  |  | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday |  |  |  | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Tasks (User stories highlighted in yellow) | Owner | Status | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | Tasks (User stories highlighted in yellow) | Owner | Status | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05
As a potential seller, I want text boxes so that I can type my inquiry and other info in | Kevin Zhang | Completed | 12 | 12 | 12 | 6 | 0 | 0 | 0 | As the business owner, I want a basic HTML outline on how the sales page should display each of its sales so that I can know how to list the jewelry on sale | Kevin Zhang | In Progress | 12 | 12 | 12 | 5 | 0 | 0 | 0
As a potential seller, I want the business owner to be able to recieve the inquiry once I submit so that he can follow up | Kevin Zhang | In Progress | 8 | 8 | 8 | 8 | 0 | 0 | 0 | As a potential client, I want instructions on how to navigate the sales page so that I will know how to do that | Kevin Zhang | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a potential seller, I want a copy of my inquiry to be sent to my email address | Kevin Zhang | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | As the business owner, I want the menu toolbar to display buttons to all the webpages so that the user may navigate to the desired page | Kevin Zhang | Completed | 3 | 3 | 3 | 3 | 0 | 0 | 0
Create and set up a PHP server and link it to the webpage | Kevin Zhang | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | As the business owner, I want the menu toolbar to have a catchy appearance so that the user can easily see and use it | Kevin Zhang | Completed | 8 | 8 | 8 | 8 | 0 | 0 | 0
Test to see whether the PHP server recieves the responses after the form is submitted | Kevin Zhang | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Troubleshoot the reason why the PHP server didn't work in getting the form submission | Kevin Zhang | In Progress | 5 | 5 | 5 | 5 | 0 | 0 | 0
As the business owner, I want an advertisement image to display so that I can attract potential clients | Kevin Zhang | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
As the business owner, I want some catchy advertising phrases so that I can attract potential clients | Kevin Zhang | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Results from Sprint 5: | [9 empty] | Results from Sprint 6:
I was able to finish around half of the backlog tasks that were assigned for this Sprint. While I was successful in creating the HTML form for submitting the inquiry, I was unable to get the PHP server working so that it could collect the data from the inquiry submission and save it in a place where I could see it. I also developed an advertising prototype image of what I should use if I'm to advertise my company to the internet. From this Sprint, I learned quite some knowledge about forms and text boxes in HTML and I also got my first experience in server-side programming in PHP. I also gained some experience in creating advertising content, though to be honest, I see ads every day on my computer so I already had a lot of prior experience no matter what. | [9 empty] | I was able to finish half of the backlog tasks that were assigned for this Sprint. The sales web page turned out to be a lot more complicated to create than the other web pages, so I was not able to finish and finalize the sales web page in this Sprint. I was, however, successful in creating the menu toolbar for each of the web pages that allows the user to click through each of the web pages. I copied and pasted the HTML and CSS code into each of the web pages. From this Sprint, even though I was not successful in half of the tasks, my attempts to be successful still allowed me to learn a lot about HTML's many different features and how to think creatively when designing an HTML website. Working to create the menu toolbar and the sales page forced my mind to think outside of the box when building a website. Slowly, my mind is truly understanding that in web development, programming is more than just coming up with a solution, it also involves being an artist for your website.
Sprint 7 Backlog
|  |  | Wednesday | Thursday | Friday | Saturday
Tasks (User stories highlighted in yellow) | Owner | Status | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09
As a business owner, I want a list of what remaining backlog for this website still needs to be finished after this course ends so that I will know what to continue to work on | Kevin Zhang | Completed | 5 | 5 | 4 | 0
As a business owner, I want a list of proposed additional features for this website so that I can start thinking about what else to add on to the website | Kevin Zhang | Completed | 4 | 4 | 4 | 0
As a business owner, I want a marketing and sales section in the business plan so that I can know how I plan to market and sell my jewelry | Kevin Zhang | Completed | 6 | 6 | 6 | 0
As a business owner, I want a funding plan section in the business plan so that I can know how I plan to fund my company | Kevin Zhang | Completed | 2 | 2 | 2 | 0
Results from Sprint 7:
I was able to finish all the backlog tasks that were assigned for this Sprint. I accomplished in documenting what remaining backlog tasks still need to be finished as well as future work that needs to be done on the website. I was also able to complete the remaining to sections of the business plan that still needed to be completed. From this Sprint, I was able to get my mind into thinking long-term about the future of this project even after this course ends. From working on the remainder of the business plan, I also now know what my marketing strategy is going to be for this company and that for now, I need to pay out of my own pocket for the very beginning of the expenses.

## Burndown Chart
| Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7
Backlog Remaining | 21 | 17 | 12 | 8 | 4
Backog Completed | 4 | 8 | 13 | 17 | 21
Backlog Planned | 25 | 25 | 25 | 25 | 25